## COs
CO # | Date | Description | Cost | Status
CO-07 | 2026-08-22 | Owner layout change | 340000 | Approved
CO-09 | 2026-09-18 | Medical gas add | 400000 | Approved
CO-12 | 2026-09-30 | Parking lot scope | 310000 | Pending