# Ironwood Ridge Constructors — Project Milestone Report

Project: Mesa Commerce Center — Building B

Date: February 20, 2026

Prepared by: Project Management

## Milestone Summary

| Structural steel complete | January 14, 2026 — Complete |
| --- | --- |
| MEP rough-in | February 28, 2026 — On track |
| Exterior cladding | March 30, 2026 — On track |
| Substantial Completion | October 18, 2026 — Owner update |
| Final Completion | November 5, 2026 — Per internal schedule |

## Substantial Completion — Schedule Note

The Substantial Completion date of October 18, 2026 was communicated to the owner in the January 28 project update email. The current internal schedule (Rev 6, February 10) reflects a Substantial Completion date of November 5, 2026, incorporating a weather delay buffer and a pending inspection cycle for the rooftop mechanical units. The project team will present the revised schedule to the owner at the February 25 OAC meeting and seek written acceptance.

## Change Orders

Active change order log total: $2,180,000 across 11 executed COs. Three additional COs are in review (CO #12–14), totaling approximately $340,000. Owner representative has verbally approved CO #12; written approval pending.

## Open Issues

Glazing subcontractor lead time — confirm delivery date by Feb 28.

Fire marshal pre-inspection scheduled for March 10.

Owner to provide final finish selections for lobby by March 1.