# QuillStack Systems — Feature Fable Delivery Update

Date: February 18, 2026

Prepared by: Product Management

## Feature Overview

Feature Fable introduces dynamic workflow branching, allowing enterprise customers to configure conditional routing in QuillStack reports without custom code.

## Target Ship Date

The Q1 roadmap deck (presented to customers and investors in January 2026) lists Fable's GA target as May 2026. The current sprint log (as of Sprint 8 completed Feb 14) forecasts a June 2026 release due to additional testing requirements for multi-tenant data isolation. Customer-facing communication will be updated once the engineering team confirms the revised forecast at the February 24 sprint review.

## Status by Workstream

| Core branching logic | Complete |
| --- | --- |
| UI configuration panel | In progress — 70% |
| Multi-tenant isolation testing | Not started — begins Sprint 9 |
| Documentation | In progress |
| Beta customer onboarding | Scheduled post-GA |

## Risks

Multi-tenant testing is the critical path item — any slip extends the June target.

Two beta customers (Harlan Corp, Meridian Trust) expecting May access; will need proactive outreach.