# Beaconline Construction Co. — Project Status Memo

Project: Harborview Office Park TI — Suite 400

Date: February 17, 2026

Prepared by: Sara Ito, Senior PM

## Schedule

As of this memo, the project is tracking toward a Substantial Completion target of March 28, 2026, per the agreed milestone schedule communicated to the owner in the February 10 weekly meeting.

Note: The schedule XLSX (Rev 4, issued February 3) reflects a re-baselined Substantial Completion of April 5, 2026 due to the delayed delivery of the custom millwork package. There is a discrepancy between the date communicated verbally and the current schedule file. Sara Ito to present updated schedule to owner at the February 24 OAC meeting.

## Change Orders

| CO #1 — Electrical panel upgrade | $28,400 — Executed |
| --- | --- |
| CO #2 — Additional data drops (8) | $14,200 — Executed |
| CO #3 — Flooring upgrade (owner) | $31,800 — Executed |
| CO #4 — Millwork revision | $44,000 — Executed |
| CO #5 — Fire sprinkler relocation | $Pending — in review |
| CO Log Total (executed) | $118,400 |

Note: The owner's representative referenced a total change order value of $124,900 in their February 10 email. This figure appears to include CO #5 (pending, not executed). Beaconline's executed CO total is $118,400.

## Budget / Margin

PM cost report projects a 6% fee margin at completion. Accounting WIP worksheet (Controller Priyanka Nair) shows tighter margin in the 3–4% range based on actual cost-to-date vs. revised budget. Will reconcile at next monthly owner billing cycle (March 1).