# Northlake Advisory Group — Engagement Status Report

Date: February 10, 2026

Prepared by: Casey Nguyen, Engagement Manager

## Active Engagements

| Client | Status |
| --- | --- |
| Cascade Logistics (Codename: Ironwood) | In delivery — Week 6 of 12 |
| Pacific Health Partners (Codename: Elm) | Kickoff complete — discovery underway |
| Regent Capital (Codename: Birch) | Proposal submitted — decision expected Feb 20 |
| Thornton Manufacturing | Retainer active — monthly advisory |

## Cascade Logistics — Utilization Note

The practice dashboard shows 78% consultant utilization for January. However, Morgan Lee spent approximately 30 hours on the Cascade engagement doing internal model builds that were coded as 'internal development' rather than client-billable. If reclassified, utilization for January would be closer to 71%. Elena Park and Finance have been notified; coding will be corrected going forward.

## Key Risks

Regent Capital decision is delayed — Birch pipeline revenue is at risk for Q1.

Pacific Health data access issues (IT procurement) may push discovery by 1 week.

Priya Shah at capacity; no additional engagements before March.

## Open Items

Elena Park to send Regent Capital follow-up by Feb 12.

Casey Nguyen to update scope memo for Pacific Health by Feb 14.

Finance to reclass Morgan Lee hours in January time log.