# LatticeOps — Feature Garnet Status Update

Date: February 14, 2026

Prepared by: Alex Chen, Head of Product

## Feature Overview

Feature Garnet is the next major product milestone for LatticeOps — a workflow automation layer allowing customers to trigger integrations directly from ops boards. It is the anchor feature for H1 2026 roadmap delivery.

## Current Status

Status: In Development — Sprint 6 of 9

## Ship Date

The H1 2026 roadmap deck (presented to board in January) lists Garnet's target release as April 2026. Based on the current sprint log (Sprint 6 closed February 7), engineering has re-forecasted the release to late May 2026 due to the API authentication rework required after the February 9 incident. This delay has not yet been communicated to customers.

## February 9 Incident — Impact on Garnet

The incident triggered a mandatory security review of all new API surface area. Garnet's integration endpoints are in scope. Sam Rivera estimates 3 additional sprints of work. The postmortem attributed root cause to vendor API instability, but internal sprint metrics show a significant backlog spike on the LatticeOps side that contributed to the degraded error handling. The auth rework addresses both.

## KPI Alignment Note

Garnet adoption metrics will be measured differently by CS and Product post-launch: CS will track 'active accounts' using Garnet at least once per week. Product will track 'weekly active users' across all accounts. Jamie Ross (CEO) has asked both teams to align on a single primary metric before the launch announcement.