## Change Orders
CO # | Date | Description | Cost | Days | Approved? | Notes
CO-01 | 2026-01-20 | Upgrade insulation | 3200 | 1 | Y
CO-02 | 2026-02-08 | Upgrade windows | 9800 | 5 | Y | Lead time risk
Total CO cost