# Birchline Insights — Engagement Scoping Memo

Date: January 6, 2026

Project: Redwood Freight Co. — Network Optimization

Prepared by: Avery Hart, Principal

## Engagement Summary

This memo confirms the agreed scope of work between Birchline Insights and Redwood Freight Co. following the contract kickoff call on January 5, 2026.

## Agreed Scope

Per the executed Statement of Work (SOW) dated December 18, 2025, this engagement is a 6-week discovery and diagnostic only. Deliverables include a current-state network map, a root-cause analysis of routing inefficiencies, and a set of prioritized recommendations. No implementation work is included in scope.

## Key Dates

| Kickoff | January 6, 2026 |
| --- | --- |
| Discovery complete | February 14, 2026 |
| Draft deliverable deck | February 21, 2026 |
| Final deliverable | February 28, 2026 |

## Budget

Estimated effort: 130–150 hours across the Birchline team. Fixed fee per SOW: $28,500. No change orders are anticipated at this time.

## Team

| Principal | Avery Hart |
| --- | --- |
| Consultant | Jordan Ng |
| Analyst | Casey Moore |

## Notes

Client requested preliminary feasibility discussion on route optimization software implementation during kickoff call. This is noted but is not in scope. Any implementation work would require a separate SOW and additional budget.