# SummitSpan Builders Group — Enterprise Project Summary

Report Period: February 2026

Prepared by: PMO

## Active Projects — Schedule Highlights

| Project | Substantial Completion |
| --- | --- |
| Cascade Tower (Portland) | July 15, 2026 — per PM weekly notes |
| Cascade Tower (Portland) | August 2, 2026 — per master schedule (re-baselined) |
| Ridgeline Logistics Park | March 30, 2026 — on track |
| Harbor Commons Multifamily | September 12, 2026 |
| Eastgate Industrial Phase 2 | December 2026 (TBD) |

## Cascade Tower — Schedule Discrepancy

The PM weekly notes for Cascade Tower, distributed to the ownership team in the January 27 project report, reference a Substantial Completion date of July 15, 2026. The master schedule (Rev 9, issued February 3) shows August 2, 2026 after re-baselining for weather delays on the podium level and a revised elevator procurement timeline. The PMO will present the revised schedule to the owner at the February 26 OAC meeting and seek written acknowledgment.

## Safety

Recordable incident rate (RIR) across active projects: 1.2 (trailing 12 months). Industry benchmark for commercial GC: ~2.0. No lost-time incidents in January.

## Financial Summary (All Projects)

| Total backlog (contracted) | $284M |
| --- | --- |
| Revenue in progress (Jan) | $18.4M |
| Gross margin (projected, portfolio) | 8.2% |